## Workflow Notes
Workflow Notes for TMP Checklists
 | Started and completed in the Stage 0 process either by Traffic Engineering Consultant (reviewed by DTOE) or District Traffic Staff. If no Stage 0 is required then would need to be completed prior to beginning the design.
 | Started and completed in the Stage 0 process either by Consultant or District Staff. If no Stage 0 is required then would need to be completed prior to beginning the design.
 | Started in the Stage 0 process either by Consultant or District Staff, re evaluated in the Stage 1 process either by Consultant or Environmental Staff. If no Stage 0 or Stage 1 then started prior to beginning design. Shall be completed by Project Manager or Designer prior to PDD.
 | Started in the Stage 0 process either by Consultant or District Staff and completed in the Stage 1 process either by Consultant or Environmental Staff. If no Stage 0 or Stage 1 then completed prior to beginning the design.
Prepared by the project manager and signed by all responsible parties prior to PDD
 | Started and completed in the Stage 0 process by personnel with training and reviewed by DOTD staff. If no Stage 0 is required then would need to be completed prior to beginning the design. Re-evaluated after Stage 1 and Stage 3.
 | Started and completed in the Stage 3 process by the designer.
 | Started in the Stage 0 process and completed by a Public Information Officer prior to PDD.

## Level 1 TMP Checklist
Level 1 Transportation Management Plan Checklist
The following list represents Transportation Management Plan (TMP) components and the percentages completed for Level 1 projects as defined in EDSM VI.1.1.8.
Directions
(a) In the left column write "Yes" if applicable or N/A if not applicable. Checkmarks denote items that are required for all projects at this level.
(b) In the right columns place the percentage completed at each submittal stage.
(c) See Workflow Notes sheet for delivery instructions.
Applicable for |  |  | Stage 0 | Stage 1 | Stage 3
this project | Level 1 TMP Components |  |  |  | Preliminary | Final | Workflow
{Required (ü)} |  |  |  |  | 60% Submittal | 90% Submittal | Notes
Analysis
|  | None Required | Percent Complete
Documentation
ü | • | TTC Details |  |  | 60% | 100% | 
| • | TTC Plan (extra ordinary circumstances) |  |  | 60% | 100% | 

## Level 2 TMP Checklist
Level 2 Transportation Management Plan Checklist
The following list represents Transportation Management Plan (TMP) components and the percentages completed for Level 2 projects as defined in EDSM VI.1.1.8.
Directions
(a) In the left column write "Yes" if applicable or N/A if not applicable. Checkmarks denote items that are required for all projects at this level.
(b) In the right columns place the percentage completed at each submittal stage.
(c) See Workflow Notes sheet for delivery instructions.
Applicable for |  |  | Stage 0 | Stage 1 | Stage 3
this project | Level 2 TMP Components |  |  |  | Preliminary | Final | Workflow
{Required (ü)} |  |  |  |  | 60% Submittal | 90% Submittal | Notes
| Analysis |  | Percent Complete
| • | Detour Analysis | 100% |  |  |  | 
| • | Queue Analysis according to Section 6A.1, Queue Analysis for Lane Closures on Interstate of the Traffic Engineering Manual | 100% |  |  |  | 
| Documentation |  | Percent Complete
ü | • | TTC Details |  |  | 50% | 100% | 
| • | TTC Plan (based on type and location of construction) |  |  | 50% | 100% | 
| • | Mitigation (if the current roadway is LOS F) | 60% | 100% |  |  | 
| • | Mitigation (if the roadway is on the Abnormal Crash Location list) | 60% | 100% |  |  | 
| • | Evacuation Strategy (if used as an evacuation route) | 100% |  |  |  | 
| • | Work Restrictions | 20% | 50% | 70% | 100% | 
ü | • | Basic Public Information release at the District level |  |  | 60% | 100% | 

## Level 3 TMP Checklist
Level 3 Transportation Management Plan Checklist
The following list represents Transportation Management Plan (TMP) components and the percentages completed for Level 3 projects as defined in EDSM VI.1.1.8.
Directions
(a) In the left column write "Yes" if applicable or N/A if not applicable. Checkmarks denote items that are required for all projects at this level.
(b) In the right columns place the percentage completed at each submittal stage.
(c) Acquire signatures from Project Manager, District Traffic Operations Engineer (DTOE), and Area Engineer.
(d) See Workflow Notes sheet for delivery instructions.
Applicable for |  |  | Stage 0 | Stage 1 | Stage 3
this project | Level 3 TMP Components |  |  |  | Preliminary | Final | Workflow
{Required (ü)} |  |  |  |  | 60% Submittal | 90% Submittal | Notes
| Section 1 - Project Description | Section 1 - Project Description | Percent Complete
ü | • | Purpose and scope | 80% | 90% | 95% | 100% | 
ü | • | Project type | 80% | 90% | 95% | 100% | 
ü | • | Project area and roadway characteristics | 80% | 90% | 95% | 100% | 
ü | • | Project vicinity map | 80% | 90% | 95% | 100% | 
ü | • | Nearby projects | 50% | 70% | 75% | 100% | 
ü | • | Project goals and constraints | 50% | 70% | 75% | 100% | 
ü | • | General construction sequencing and timeline |  | 80% | 90% | 100% | 
Section 2 - Alternate Route Analysis
ü | • | Alternative route vicinity map | 100% |  |  |  | 
| • | Brief explanation of why it is necessary to close the roadway (if closing roadway) | 75% | 85% | 95% | 100% | 
ü | • | Assessment of the detour route/alternate route | 100% |  |  |  | 
ü | • | A plan to gather and address safety and mobility concerns on the alternate route | 100% |  |  |  | 
ü | • | Conclusions to alternate route analysis | 100% |  |  |  | 
Section 3 - Public Information Plan
ü | • | Public Information and Outreach Strategies | 25% | 50% | 70% | 100% | 
| • | Motorist Information Strategies | 25% | 50% | 70% | 100% | 
Section 4 - Stakeholder Involvement (if required)
ü | • | List of stakeholders with their contact information (i.e. TMC operators, law enforcement, emergency response personnel, local jurisdictions, business owners, etc.) | 50% | 100% |  |  | 
ü | • | Documentation of meetings and/or interviews |  | 100% |  |  | 
Section 5 - TMP Roles and Responsibilities (with signatures and resources)
ü | • | Project Engineer (PE) |  |  | 30% | 95%
ü | • | Area Engineer |  |  | 30% | 95%
ü | • | District Traffic Operations Engineer (DTOE) |  |  | 30% | 95%
ü | • | Public Information Officer (PIO) |  |  | 30% | 95%
ü | • | Transportation Managament Center (TMC) |  |  | 30% | 95%
| • | Other -
| • | Other -
Section 6 - Traffic Data
ü | • | 7 day 24 hour counts | 100% |  |  |  | 
ü | • | Peak hour counts | 100% |  |  |  | 
ü | • | Analysis for existing conditions and proposed closure times | 100% |  |  |  | 
| • | Analysis for proposed mitigation |  |  |  |  | 
Section 7 - Safety Analysis
ü | • | Impact Area | 100% |  |  |  | 
ü | • | Summarized crash data (3 years) | 100% |  |  |  | 
ü | • | Baseline safety performance | 100% |  |  |  | 
| • | Crash data analysis |  |  |  |  | 
| • | Mitigation analysis |  |  |  |  | 
| • | Crash data summary list |  |  |  |  | 
Section 8 - Temporary Traffic Control
ü | • | TTC Details (in plans) |  |  | 60% | 100% | 
ü | • | TTC Plans (in plans) |  |  | 60% | 100%
|  | A. A layout of the temporary traffic control plan |  |  |  |  | 
B. Proposed construction phasing
| • | Other Traffic Control Devices (PCMS, etc.) |  |  |  |  | 
Section 9 - Work Zone Impact Management Strategies
ü | • | Project Coordination, Contracting, and Innovative Construction Strategies | 25% | 50% | 70% | 100% | 
ü | • | Transportation Operations Strategies | 25% | 50% | 70% | 100% | 
ü |  | A. Demand Management Strategies | 25% | 50% | 70% | 100% | 
ü |  | B. Corridor/Network Management Strategies | 25% | 50% | 70% | 100% | 
ü |  | C. Work Zone Safety Management Strategies | 25% | 50% | 70% | 100% | 
ü | • | Traffic/incident management and enforcement strategies | 25% | 50% | 70% | 100% | 
ü | • | Contingency plan/evacuation scenario | 25% | 50% | 70% | 100% | 
ü | • | Construction Alternatives | 25% | 50% | 70% | 100% | 
ü |  | A. Documentation of all costs, benefits, alternatives, | 25% | 50% | 70% | 100% | 
ü |  | and who is responsible for each cost
ü |  | B. A list of costs shared in coordination with other | 25% | 50% | 70% | 100% | 
ü |  | projects
ü | • | TMP Implementation Cost | 25% | 50% | 70% | 100% | 

## Level 4 TMP Checklist
Level 4 Transportation Management Plan Checklist
The following list represents Transportation Management Plan (TMP) components and the percentages completed for Level 4 projects as defined in EDSM VI.1.1.8
Directions
(a) In the left column write "Yes" if applicable or N/A if not applicable. Checkmarks denote items that are required for all projects at this level.
(b) In the right columns place the percentage completed at each submittal stage.
(c) Acquire signatures from Project Manager, District Traffic Operations Engineer (DTOE), and Area Engineer.
(d) See Workflow Notes sheet for delivery instructions.
Applicable for |  |  | Stage 0 | Stage 1 | Stage 3
this project | Level 4 TMP Components |  |  |  | Preliminary | Final | Workflow
{Required (ü)} |  |  |  |  | 60% Submittal | 90% Submittal | Notes
| Section 1 - Project Description |  | Percent Complete
ü | • | Purpose and scope | 80% | 90% | 95% | 100% | 
ü | • | Project type | 80% | 90% | 95% | 100% | 
ü | • | Project area and roadway characteristics | 80% | 90% | 95% | 100% | 
ü | • | Project vicinity map | 80% | 90% | 95% | 100% | 
ü | • | Nearby projects | 50% | 70% | 75% | 100% | 
ü | • | Project goals and constraints | 50% | 70% | 75% | 100% | 
ü | • | General construction sequencing and timeline |  | 80% | 90% | 100% | 
Section 2 - Alternate Route Analysis
ü | • | Alternative route vicinity map | 100% |  |  |  | 
| • | Brief explanation of why it is necessary to close the roadway (if closing roadway) | 75% | 85% | 95% | 100% | 
ü | • | Assessment of the detour route/alternate route | 100% |  |  |  | 
ü | • | A plan to gather and address safety and mobility concerns on the alternate route including conclusions to the analysis | 100% |  |  |  | 
ü | • | Conclusions to alternate route analysis | 100% |  |  |  | 
Section 3 - Public Information Plan
ü | • | Public Information and Outreach Strategies | 25% | 50% | 70% | 100% | 
| • | Motorist Information Strategies | 25% | 50% | 70% | 100% | 
Section 4 - Stakeholder Involvement (if required)
ü | • | List of stakeholders with their contact information (i.e. TMC operators, law enforcement, emergency response personnel, local jurisdictions, business owners, etc.) | 50% | 100% |  |  | 
ü | • | Documentation of meetings and/or interviews |  | 100% |  |  | 
Section 5 - TMP Roles and Responsibilities (with signatures and resources)
ü | • | Project Engineer (PE) |  |  | 30% | 95%
ü | • | Area Engineer |  |  | 30% | 95%
ü | • | District Traffic Operations Engineer (DTOE) |  |  | 30% | 95%
ü | • | Public Information Officer (PIO) |  |  | 30% | 95%
ü | • | Transportation Management Center (TMC) |  |  | 30% | 95%
| • | Other -
| • | Other -
Section 6 - Traffic Data
ü | • | 7 day 24 hour counts | 100% |  |  |  | 
ü | • | Queue Analysis according to Section 6A.1, Queue Analysis for Lane Closures on Interstate of the Traffic Engineering Manual | 100% |  |  |  | 
Section 7 - Safety Analysis
ü | • | Impact Area | 100% |  |  |  | 
ü | • | Summarized crash data (3 years) | 100% |  |  |  | 
ü | • | Baseline safety performance | 100% |  |  |  | 
| • | Crash data analysis |  |  |  |  | 
| • | Mitigation analysis |  |  |  |  | 
| • | Crash data summary list |  |  |  |  | 
Section 8 - Temporary Traffic Control
ü | • | TTC Details (in plans) |  |  | 60% | 100% | 
ü | • | TTC Plans (in plans) |  |  | 60% | 100%
|  | A. A layout of the temporary traffic control plan |  |  |  |  | 
B. Proposed construction phasing
| • | Other Traffic Control Devices (PCMS, etc.) |  |  |  |  | 
Section 9 - Work Zone Impact Management Strategies
ü | • | Project Coordination, Contracting, and Innovative Construction Strategies | 25% | 50% | 70% | 100% | 
ü | • | Transportation Operations Strategies | 25% | 50% | 70% | 100% | 
ü |  | A. Demand Management Strategies | 25% | 50% | 70% | 100% | 
ü |  | B. Corridor/Network Management Strategies | 25% | 50% | 70% | 100% | 
ü |  | C. Work Zone Safety Management Strategies | 25% | 50% | 70% | 100% | 
ü | • | Traffic/incident management and enforcement strategies | 25% | 50% | 70% | 100% | 
ü | • | Contingency plan/evacuation scenario | 25% | 50% | 70% | 100% | 
ü | • | Construction Alternatives | 25% | 50% | 70% | 100% | 
ü |  | A. Documentation of all costs, benefits, alternatives, | 25% | 50% | 70% | 100% | 
ü |  | and who is responsible for each cost
ü |  | B. A list of costs shared in coordination with other | 25% | 50% | 70% | 100% | 
ü |  | projects
ü | • | TMP Implementation Cost | 25% | 50% | 70% | 100% | 