## Sheet1
Project No.
Control Section
Parish
District
Revised 08/02/16
Plan Constructability Review
PRNI, PRNF, PR PM and TSM projects
PLAN CONSTRUCTABILITY REVIEW
Purpose:
| ▪ | To provide information to assist in producing quality plans
| ▪ | To provide a history of information that is easily accessible
| ▪ | To provide questions that would stimulate discussion of potentially problematic areas
| ▪ | To provide questions that will stimulate checking for all details and items required to complete the project
| ▪ | To provide aid during design for QA / QC
Instructions for completing the form:
| ▪ | The Preliminary Design portion of the form shall be filled out and signed by the Design Engineer or Construction Coordinator
and a copy of the form shall be submitted with the preliminary plans to the Construction Section and PRR unit.
| ▪ | The original form, with Preliminary Design portion complete, and preliminary plans shall be sent to the Project Engineer.
| ▪ | The Final Construction portion shall be filled out and signed by the Project Engineer and reviewed and signed by the Area
Engineer based on the preliminary plan submittal. The Project Engineer will address any comments from the Design Engineer
or Construction Coordinator and return the completed form to the Design Engineer. The original document will be submitted
with the final plans to the PRR Unit, with a copy transmitted to the Construction Section.
| ▪ | If an answer to the questions is in a blue box (or lightly shaded if in black and white), a comment is NOT required.
| ▪ | Most questions are designed such that a "NO" answer will require comments on what is missing or needed.
| ▪ | Most questions answered with "YES" means the plans meet the project needs or a follow up question is required.
| ▪ | If comment is lengthy, show reference number on notes page for easy reference.
| ▪ | Design Engineers will ensure all comments are addressed and copy all reviewers.
| ▪ | Each review is considered complete when all comments are addressed.
| ▪ | If question is answered N/A, question is not applicable to project.
PLAN CONSTRUCTABILITY REVIEW
STATE PROJECT NO. | [5 empty] | ROUTE NO.
CONTROL SECTION | [5 empty] | PARISH
DATE OF SITE VISIT | [5 empty] | DISTRICT
Description |  |  |  | Preliminary Plans |  | Final Plans |  | N/A
|  |  |  | Design |  | Construction
|  |  |  | Y | N | Y | N |  | Comment | Response
I. TITLE SHEET
1. Are limits shown on Title Sheet in agreement with
typical sections and summary sheets?
2. Are project limit exceptions noted? (RR, Bridge, etc.)
3. Are all applicable standard plans noted?
4. Is the traffic data current and does it reflect
actual conditions?
5. Are all Control Sections shown?
II. TYPICAL SECTION SHEETS
1. Does the proposed pavement treatment match
recommendations in PMS?
1a. If no, has justification been submitted?
2. Is the existing typical section shown, along with the
existing cross slope?
3. Are pavement markings and lane widths shown?
4. Are stations/limits shown?
DESCRIPTION |  |  |  | Preliminary Plans |  | Final Plans |  | N/A
|  |  |  | Design |  | Construction
|  |  |  | Y | N | Y | N |  | Comment | Response
5. Are limits of milling shown?
5a. If in PR PM program, is milling restricted to tie-ins?
6. Are ESALs shown?
7. Is laboratory information included for existing roadway?
8. Are under drains needed / included in the plans?
9. Are Design Exceptions required / noted?
10. Is earthwork / base course construction required?
10a. Is it constructible as shown in the plans?
11. Are all transitions, both horizontal and vertical, accounted
for in the plans?
12. Are exceptions shown for RR, Bridges, etc.?
A. EARTHWORK
1. Is method of payment for earthwork / borrow satisfactory?
B. DRAINAGE
1. Will project drain properly during construction?
2. Will existing ditch cleaning be required?
2a. If yes, can this be done by maintenance forces prior to letting?
letting?
2b. If needed, are the limits and pay items included?
3. Is there identification and adequacy of all drainage items and
and quantities?
4. Is there a method to connect new and existing drainage structures?
structures?
5. Is bedding material item included?
6. Is pH and resistivity and gage table information included in
plans?
7. If new or altered drainage structures are planned, are utility
adjustments required?
8. Will existing pipe lengths and headwalls accommodate changes in
foreslopes and pavement width?
C. EROSION CONTROL
1. Are temporary erosion control items been included?
2. Are permanent erosion control items required?
2a. If yes, list types.
DESCRIPTION |  |  |  | Preliminary Plans |  | Final Plans |  | N/A
|  |  |  | Design |  | Construction
|  |  |  | Y | N | Y | N |  | Comment | Response
D. MISCELLANEOUS
1. Is an item included for necessary removals?
2. Are there any salvageable materials defined?
2a. If yes, has location for hauling / stockpiling been defined?
3. Is traffic maintenance aggregate required?
3a. If yes, how much?
4. If amount of contractor retained cold planed asphalt is <75% of
of total RAP quantity, has approval been obtained?
5. Is pavement patching required?
5a. Have quantities been field verified?
5b. If in PR PM program, is patching <1% of total SY?
6. Is an item for saw cutting included for removal of concrete
drives if they are not being replaced?
7. Are exceptions shown and properly depicted in tables? (RR, Bridge, etc.)
Bridges, etc.)
8. Do pay items conform to current "Master Item List" / Site Manager?
Manager?
9. Have specialty items been given appropriate numbers compliant with
compliant with Site Manager and ASHTO*ware?
10. Is it necessary to create any new NS items?
10a. If yes, has information been sent to Contracts and
Specifications?
11. Is a project site laboratory or project site laboratory (equipped)
required? Please list type.
12. Do loop detectors or ATR exist?
12a. If yes, will existing equipment be destroyed by construction?
12b. If equipment is being replaced, are all pay items included (i.e.
conduit, junction boxes, etc.)?
12c. If equipment is being replaced, are traffic signal details included?
12d. Has Traffic Section requested video detection?
13. Are there notes and/or items covering pay for traffic control items?
DESCRIPTION |  |  |  | Preliminary Plans |  | Final Plans |  | N/A
|  |  |  | Design |  | Construction
|  |  |  | Y | N | Y | N |  | Comment | Response
IV. ADA ASSESSMENT
1. ADA data for project has been reviewed using database
in Sharepoint.
2. Deficiencies that can be corrected have been addressed.
3. Is a removal of walks and drives item necessary for
installation of handicapped ramps?
4. Is an item included for a suitable tie-in?
V. SAFETY ASSESSMENT
1. Crash data for project has been reviewed.
2. Has an RSA checklist been completed?
2a. If needed, has RSA been conducted?
2b. Are recommendations from RSA included in plans?
3. Have improvements from the PRR Program Baseline Countermeasures
Checklist been considered in the plans?
VI. GEOMETRIC DETAILS
3. Are required superelevation tables and diagrams in the plans?
4. Have necessary items to correct cross slopes been incorporated
into the plans?
5. Will changes in the superelevation affect driveway or property
access?
VII. SEQUENCE OF CONSTRUCTION
1. Is a TMP Level 2, 3 or 4 required?
2. Is thru traffic to be maintained?
2a. If no, are detour routes provided?
3. Do striping quantities reflect all traffic sequencing?
4. Are there adequate accommodations for intersecting and crossing
traffic?
5. Have pedestrian and bicycle accommodations been addressed?
6. Have maintenance of traffic restrictions (e.g. lane closure, general construction or peak hour
general construction or peak hour restrictions in urban areas,
schools, festivals, harvesting, RS 48:279 - Night time work) been identified and placed into
identified and placed in ProjectWise for use in the proposal preparation?
preperation?
DESCRIPTION |  |  |  | Preliminary Plans |  | Final Plans |  | N/A
|  |  |  | Design |  | Construction
|  |  |  | Y | N | Y | N |  | Comment | Response
7. Are items for temporary safety device requirements and provisions
provisions included (guard rail, attenuators, barrier rail, etc.)?
8. Are there conflicts between existing and new surfacing being used
to maintain traffic (drop-offs >2", guard rail, etc.)?
9. If existing parking is affected, have accommodations been made for
temporary and permanent parking?
VIII. GENERAL
1. Is the project constructible with typical construction equipment
(tandem trucks, mtv's, etc.)?
2. Are there any bridges with posted weights within the project area
that will limit the type of construction equipment used?
2a. If yes, explain.
3. Are appropriate general notes and special provisions shown for
construction?
4. Are all applicable special details included in plans?
5. If finish grade elevation is increased, will adjustments be needed
for the following?
- intersections
- curbs
- catch basins
- manholes / valves
- bridge railing / guard rail
- shoulders
- other
6. If overlaying a bridge, has Bridge Design been consulted?
7. Are plans clear and legible?
8. Do specifications support the plans?
9. Do current site conditions conform to those represented in plans?
(patching quantities, drives, etc.)?
DESCRIPTION |  |  |  | Preliminary Plans |  | Final Plans |  | N/A
|  |  |  | Design |  | Construction
|  |  |  | Y | N | Y | N |  | Comment | Response
10. Have environmental safeguards on dust control, erosion, noise, and
disposal of wastes been addressed?
11. Are there horizontal or vertical clearance issues within the work
zone (overhead utilities, guy wires, tree canopies, power poles, bridges, etc.)
bridges, etc.)?
12. Have all encroachments been addressed?
13. Have previous commitments been addressed (City/State or agreements,
RR agreements, decisions from stage 0, etc.) ?
14. Has a Contract Time Worksheet been completed?
15. Is an assembly period recommended?
15a. If yes, how many days?
16. If turn lanes are added, will the following apply:
16a. Are utility adjustments required?
16b. Do any right-of-way issues need to be addressed?
16c. Are Geometric Detail Sheets or Plan/Profile Sheets needed?
17. Is assistance needed for construction administration? (CE&I)
17a. If yes, specify needs.
Please print name, then sign.
Preliminary Review by Designer / Construction Coordinator | [6 empty] | Date
Final Review by Project Engineer | [6 empty] | Date
Constructability Review by Area Engineer | [6 empty] | Date
Item | Comment
No.