## TCLB
SPN: | H.000000.6 |  |  |  | work performed (check all that apply)
TCS Name: | John Doe | All Day: | yes
TCS SM ID: | cccc0000 |  |  |  | x | no work | saw-cutting roadway
TCT Name (delegated): | n/a | Delegated: | no |  |  | site clean-up | saw-cutting driveway
Log book date: | 2023-05-20 |  |  |  |  | asphalt wearing | drainage
Date entered: | 2023-05-22 | inspection time |  |  |  | asphalt binder | miscellaneous concrete
TCS arrival time: | 5:00 | 1st: | 6:00 |  |  | asphalt base | concrete barrier rail
TCS departure time: | 18:00 | 2nd: | 12:00 |  |  | pcc roadway (concrete) | curb & gutter
Weather: | clear | 3rd: | 17:00 |  |  | profilographing | guardrail
Low Temp (°F): | 70 |  |  |  |  | cold planing | bridge
|  | speed limit (MPH) |  |  |  | grinding | its work
|  | existing: | 55 |  |  | patching | turn lane
|  | reduced: | 45 |  |  | lime treatment | ramp
|  | special: |  |  |  | soil-cement | elevated island
[6 empty] | stone base | utilities
[6 empty] | premixing | detour road
[6 empty] | rumble strip | striping
traffic control plan used | [5 empty] | blank #1 | blank #2
standards used | TTC | station
|  | begin | end |  | work performed - description
sheet number | 23 | 120000 | 150000 |  | no work performed today
sheet number
sheet number
sheet number
devices on project | yes
| # used | correct | station |  |  | date maint/clean/repair | date installed
pilot vehicles: | 0 | n/a |  |  |  | n/a | n/a
flaggers: | 0 | n/a |  |  |  | n/a | n/a
construction signing: | 5 | yes | begin/end |  |  | 2023-04-01 | 2023-04-01
barricades: | 10 | yes | 130000 |  |  | 2023-05-10 | 2023-04-01
drums: | 25 | yes | 130000 |  |  | 2023-05-10 | 2023-04-01
vertical panels: | 25 | yes | 130000 |  |  | 2023-04-01 | 2023-04-01
tubular traffic markers: | 0 | n/a |  |  |  | n/a | n/a
super-cones: | 100 | yes | 130000 |  |  | 2023-05-10 | 2023-04-01
tma: | 1 | yes | 130000 |  |  | 2023-04-01 | 2023-04-01
arrow board (type c): | 3 | yes | 130000 |  |  | 2023-04-01 | 2023-04-01
barrier wall: | 0 | n/a |  |  |  | n/a | n/a
a/b lights: | 30 | yes | 130000 |  |  | 2023-05-10 | 2023-04-01
c lights: | 15 | yes | 130000 |  |  | 2023-05-10 | 2023-04-01
conflicting pavement markings removed for long term closures? |  |  | yes
other devices used: | [5 empty] | general notes:
n/a | [5 empty] | no work on project, long-term EB closure in good condition, no adjustment or repairs needed
PCMS (Portable Changeable Message Sign) |  | correct | station |  |  | date maint/clean/repair | date message approved
PCMS #1 |  | yes | 130000 |  |  | 2023-05-10 | 2023-04-01
lane | screen 1-line 1 | MON 5-20 |  | screen 2-line 1
closed | screen 1-line 2 | TUE 5-21 |  | screen 2-line 2
tonight | screen 1-line 3 | 5PM-4AM |  | screen 2-line 3
|  | correct | station |  |  | date maint/clean/repair | date message approved
PCMS #2 |  | n/a
| screen 1-line 1 |  |  | screen 2-line 1
| screen 1-line 2 |  |  | screen 2-line 2
| screen 1-line 3 |  |  | screen 2-line 3
|  | correct | station |  |  | date maint/clean/repair | date message approved
PCMS #3 |  | n/a
| screen 1-line 1 |  |  | screen 2-line 1
| screen 1-line 2 |  |  | screen 2-line 2
| screen 1-line 3 |  |  | screen 2-line 3
|  | correct | station |  |  | date maint/clean/repair | date message approved
PCMS #4 |  | n/a
| screen 1-line 1 |  |  | screen 2-line 1
| screen 1-line 2 |  |  | screen 2-line 2
| screen 1-line 3 |  |  | screen 2-line 3
|  | correct | station |  |  | date maint/clean/repair | date message approved
PCMS #5 |  | n/a
| screen 1-line 1 |  |  | screen 2-line 1
| screen 1-line 2 |  |  | screen 2-line 2
| screen 1-line 3 |  |  | screen 2-line 3
|  | correct | station |  |  | date maint/clean/repair | date message approved
PCMS #6 |  | n/a
| screen 1-line 1 |  |  | screen 2-line 1
| screen 1-line 2 |  |  | screen 2-line 2
| screen 1-line 3 |  |  | screen 2-line 3
Miscellanous
Deficiencies found/corrected (date/time/personnel found/corrected):
no deficiencies found today, no deficiencies outstanding
pedestrian accomodations: | n/a | explanation: | work on interstate, no pedestrians
attenuators: | yes | type: | RoadSafe SLED
water checked: | yes
crash | no | description: | n/a
begin station:
end station:
photos/videos: | n/a
attachments to this diary: | n/a
other notes: | n/a
I certify this report is accurate to the best of my knowledge.
Trey Charles Smith |  | trey c smith |  |  |  |  | 2023-05-20
Name (print) |  | Name (signed) |  |  |  |  | Date